## Risk Register
Register ID | Risk Description | Likelihood | Impact | Risk Score | Owner | Mitigation Status | Last Updated | Next Review Date
R-0001 | Laptop theft results in sensitive client data exposure | 4 | 5 | 20 | IT Security Lead | In Progress (Disk encryption rollout underway) | 2026-01-04 | 2026-02-02
R-0002 | Third-party SaaS vendor lacks updated SOC2 audit | 3 | 4 | 12 | GRC Analyst | Not Started (Due dilligence begins next week) | 2026-01-01 | 2026-02-17
R-0003 | Unpatched software leads to system vulnerability exploitation | 3 | 5 | 15 | IT Security Lead | Scheduled (Monthly patching cycle being formalised) | 2026-01-16 | 2026-02-16
R-0004 | Phishing attack results in employee credential compromise | 4 | 4 | 16 | Cyber Awareness Manager | In Progress (Security awareness training rollout) | 2026-02-06 | 2026-02-15
R-0005 | Misconfigured cloud storage exposes internal documents | 3 | 5 | 15 | Cloud Services Manager | In Progress (Access review and configuration audit underway) | 2026-02-06 | 2026-02-15
R-0006 | Third‑party vendor suffers a data breach affecting shared information | 3 | 4 | 12 | IT Operations Manager | In Progress (Backup policy update and automated backups being implemented) | 2026-02-06 | 2026-02-25
R-0007 | Weak password practices lead to unauthorised account access | 3 | 4 | 12 | IT Security Lead | Planned - Password policy update scheduled | 2026-02-10 | 2026-03-10
R-0008 | Phishing email results in malware installation on staff device | 4 | 4 | 16 | Cyber Awareness Manager | In Progress - Phishing simulation training underway | 2026-02-10 | 2026-02-24
R-0009 | Misplaced USB drive containing unencrypted files | 2 | 5 | 10 | Data Protection Officer | Planned - USB encryption policy rollout | 2026-02-10 | 2026-03-12
R-0010 | Cloud misconfiguration exposes internal documents publicly | 3 | 5 | 15 | Cloud Services Manager | In Progress - Configuration audit ongoing | 2026-02-10 | 2026-02-20
R-0011 | Delayed software patching leaves systems vulnerable | 4 | 4 | 16 | IT Operations Manager | In Progress - Automated patching deployment | 2026-02-10 | 2026-03-05
R-0012 | Third-party vendor fails to meet security requirements | 2 | 4 | 8 | Vendor Management Lead | Planned - Vendor security questionnaire pending | 2026-02-10 | 2026-03-15
R-0013 | Accidental email sent to wrong recipient exposes personal data | 3 | 4 | 12 | Data Protection Officer | In Progress - Email DLP rules being configured | 2026-02-10 | 2026-02-28
R-0014 | Server outage disrupts business operations | 2 | 5 | 10 | IT Infrastructure Lead | Planned - High-availability upgrade proposal | 2026-02-10 | 2026-03-18
R-0015 | Inadequate access reviews allow former staff to retain system access | 3 | 5 | 15 | HR & IT Access Control | In Progress - Quarterly access review process | 2026-02-10 | 2026-02-25
R-0016 | Weak Wi-Fi security enables unauthorised network access | 3 | 4 | 12 | Network Administrator | Planned - WPA3 upgrade and segmentation | 2026-02-10 | 2026-03-14
R-0017 | Critical database breach exposes sensitive client records | 5 | 5 | 25 | IT Security Lead | In Progress - Emergency incident response underway | 2026-02-10 | 2026-02-12
R-0018 | Ransomware attack encrypts core business systems | 5 | 5 | 25 | IT Operations Manager | Planned - Network segmentation and EDR upgrade | 2026-02-10 | 2026-02-20
R-0019 | Major cloud outage disrupts customer-facing services | 4 | 5 | 20 | Cloud Services Manager | In Progress - Multi-region redundancy implementation | 2026-02-10 | 2026-02-18
R-0020 | Insider threat intentionally exfiltrates confidential data | 4 | 5 | 20 | Data Protection Officer | Planned - Privileged access monitoring rollout | 2026-02-10 | 2026-02-25
R-0021 | Failure of primary data centre causes full service downtime | 5 | 4 | 20 | IT Infrastructure Lead | In Progress - Disaster recovery testing | 2026-02-10 | 2026-02-28
R-0022 | Minor software bug causes occasional UI display issues | 1 | 2 | 2 | Product Team Lead | Planned - Patch scheduled for next sprint | 2026-02-10 | 2026-03-20
R-0023 | Non-critical documentation stored in outdated format | 1 | 1 | 1 | Compliance Officer | Planned - Documentation refresh project | 2026-02-10 | 2026-03-30
R-0024 | Low-impact printer malfunction in admin office | 1 | 1 | 1 | Facilities Manager | In Progress - Replacement ordered | 2026-02-10 | 2026-03-15
R-0025 | Occasional delays in internal email delivery | 2 | 1 | 2 | IT Support Lead | Planned - Mail server optimisation | 2026-02-10 | 2026-03-22
R-0026 | Outdated training material on intranet | 1 | 2 | 2 | HR Training Manager | In Progress - Content update underway | 2026-02-10 | 2026-03-12